## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US001 | As a data engineer, I want to collect and preprocess transaction data so that it can be used for model training. | Must Have | Dataset availability | Backend Team | Completed
Sprint 2 | Sprint 2 | US002 | As a data scientist, I want to train an ML model that predicts fraudulent transactions using historical data. | Must Have | Cleaned data | Backend Team | Completed
Sprint 3 | Sprint 3 | US003 | As an AI developer, I want to integrate an LLM to provide human-readable explanations for fraud predictions. | Should Have | Trained model | Backend Team | Completed
Sprint 4 | Sprint 4 | US004 | As a frontend developer, I want to create an interactive dashboard that displays transaction risk results and performance metrics. | Must Have | APIs ready | Frontend Team | Completed
Sprint 4 | Sprint 4 | US005 | As a DevOps engineer, I want to deploy and integrate the entire system in a test environment for demonstration. | Could Have | Backend & frontend integration | Both Teams | Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US001 | T1 | Collect transaction dataset and verify structure | 2025-09-10 | 2025-09-11 | Backend1 | Data Collection | Done | 6 | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
US001 | T2 | Clean missing values and normalize features | 2025-09-12 | 2025-09-14 | Backend2 | Data Collection | Done | 10 | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
US002 | T3 | Train ML model (Random Forest) for fraud prediction | 2025-09-15 | 2025-09-18 | Backend3 | Model Training | Done | 12 | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
US003 | T4 | Integrate LLM to generate prediction explanations | 2025-09-19 | 2025-09-21 | Backend4 | AI Integration | Done | 8 | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
US004 | T5 | Create frontend dashboard for fraud prediction visualization | 2025-09-22 | 2025-09-25 | Frontend1 | UI Development | Done | 10 | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE
US005 | T6 | Deploy backend and frontend to test environment | 2025-09-26 | 2025-09-28 | Both Teams | Deployment | Done | 8 | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 2 | Day 3 | ML model taking too long to train due to large dataset | Reduced features and applied stratified sampling
Sprint 2 | Day 4 | API returning 500 error during prediction | Debugged endpoint, fixed missing JSON key
Sprint 3 | Day 2 | LLM responses too long and inconsistent | Applied temperature control and prompt optimization
Sprint 4 | Day 1 | Frontend not fetching data due to CORS issue | Enabled CORS in FastAPI backend

## Retrospection
SL | Sprint | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 2025-09-10 | 2025-09-14 | Backend Team | Document preprocessing steps clearly | Rushing into training without validation | Collaborating during data cleaning | Created shared preprocessing document
2 | 2 | 2025-09-15 | 2025-09-21 | Backend Team | Use version control for model files | Using large data without sampling | Testing each version before training | Implemented model versioning
3 | 3 | 2025-09-22 | 2025-09-25 | AI Team | Write prompts clearly for LLM | Using unstructured prompts | Evaluating prompt output for accuracy | Finalized best-performing prompts
4 | 4 | 2025-09-10 | 2025-09-14 | Frontend+Backend | Prepare documentation parallelly | Waiting till the end to test integration | Regular cross-team syncs | Weekly integration meetings scheduled