## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Backend Team | 2025-09-16 | API returned 500 error when no transaction ID was provided | Sprint 2 | Backend Team | Functional | Added input validation to check for empty transaction ID before model call | 2025-09-17 | Closed | Handled using try-except and input schema validation
2 | Frontend Team | 2025-09-18 | Dashboard graph not updating after prediction result | Sprint 2 | Frontend Team | UI Integration | Added state refresh in React after API call completion | 2025-09-19 | Closed | Graph now updates dynamically post prediction
3 | Backend Team | 2025-09-20 | Model predictions inconsistent after multiple API calls | Sprint 2 | Backend Team | Logic | Fixed model reloading issue by loading model once globally | 2025-09-21 | Closed | Improved model loading logic for better performance
4 | Frontend Team | 2025-09-24 | Frontend CORS error while calling backend API | Sprint 3 | Backend Team | Integration | Enabled CORS headers in Flask backend using flask-cors | 2025-09-25 | Closed | Frontend and backend communication successful
5 | Backend Team | 2025-09-26 | LLM returning incomplete explanation in fraud reasoning | Sprint 3 | Backend Team | AI/LLM | Adjusted prompt structure and reduced temperature to improve clarity | 2025-09-27 | Closed | LLM responses more consistent now
6 | Frontend Team | 2025-09-28 | Prediction table displaying wrong confidence score | Sprint 3 | Frontend Team | UI/Functional | Fixed JSON key mapping in frontend API response | 2025-09-29 | Closed | Confidence score now displays correctly
7 | Testing Team | 2025-09-29 | Dashboard loading time too high when fetching data | Sprint 4 | Both Team | Performance | Added backend pagination & frontend lazy loading | 2025-09-30 | Closed | Dashboard now loads efficiently
8 | Frontend Team | 2025-10-01 | Model performance metrics table not showing updated values | Sprint 4 | Frontend Team | UI/Data Sync | Triggered metric fetch API after every model retrain | 2025-10-02 | Closed | Metrics table updates automatically
9 | QA_Team | 2025-10-03 | Fraud/Legit chart overlapping on mobile view | Sprint 4 | Frontend Team | UI Responsive | Fixed responsive layout using CSS grid and media queries | 2025-10-04 | Closed | Dashboard mobile-friendly now
10 | Backend Team | 2025-10-04 | Deployment failed on Render due to missing environment variables | Sprint 4 | Backend Team | Deployment | Configured .env variables and updated deployment script | 2025-10-05 | Closed | Successfully deployed backend service

## Sheet2
Logical
User Interface
Maintainability
Standards
Others